## Modules
Module | Status
Auth_Authorisation | Not Started
Recruiter_Management | Not Started
Client_Management | Not Started
Job_Application_Management | Not Started
Duplicate_Detection | Not Started
Analytics_Dashboard | Not Started
Shift_Logic | Not Started
Branding_UI | Not Started

## Auth_Authorization
Task | Remark | Date | Status | Completed
Setup Database Schema for Users and Roles | Define tables for users, roles, and permissions |  | Not Started | FALSE
Implement User Registration and Password Hashing | Use bcrypt or similar for secure hashing |  | Not Started | FALSE
Implement Login API and JWT Generation | Return JWT token on successful login |  | Not Started | FALSE
Implement Role-Based Access Control (RBAC) middleware | Protect routes based on Admin/Recruiter roles |  | Not Started | FALSE
Create Protected Routes for Admin and Recruiter | Ensure secure access to endpoints |  | Not Started | FALSE
Develop Frontend Login Page | Create UI for user authentication |  | Not Started | FALSE
Integrate Frontend with Auth APIs | Connect UI with backend authentication |  | Not Started | FALSE

## Recruiter_Management
Task | Remark | Date | Status | Completed
Setup Recruiter Database Table | Define schema for recruiter details |  | Not Started | FALSE
Create API to Add New Recruiter (Admin only) | Endpoint for Admin to create recruiters |  | Not Started | FALSE
Create API to Edit Recruiter Details | Endpoint to update recruiter info |  | Not Started | FALSE
Create API to Activate/Deactivate Recruiter | Endpoint to toggle recruiter status |  | Not Started | FALSE
Create API to Fetch Recruiter Information and Stats | Include profile count and link count per shift |  | Not Started | FALSE
Develop Admin UI for Recruiter Management | UI for Admin to perform CRUD operations |  | Not Started | FALSE
Implement Optional Soft Delete for Recruiters | Allow safe deletion without data loss |  | Not Started | FALSE

## Client_Management
Task | Remark | Date | Status | Completed
Setup Client Profile Database Schema | Include Name, Email, Phone, Tech/Skill, Notes, Recruiter |  | Not Started | FALSE
Create API to Add New Client Profile | Endpoint to create a new profile |  | Not Started | FALSE
Create API to Edit Client Profile Details | Endpoint to update profile info |  | Not Started | FALSE
Create API to Assign Profile to Recruiter | Link profile to a specific recruiter |  | Not Started | FALSE
Develop Recruiter UI for Managing Profiles | UI for recruiters to view and edit assigned profiles |  | Not Started | FALSE
Implement Filtering and Searching for Profiles | Allow easy lookup of profiles |  | Not Started | FALSE

## Job_Application_Management
Task | Remark | Date | Status | Completed
Setup Job Application Database Schema | Include Profile, Recruiter, Link, Company, Title, Portal, Timestamp, Status |  | Not Started | FALSE
Create API to Submit New Job Application | Endpoint to save application details |  | Not Started | FALSE
Create API to Fetch Application History | Endpoint to retrieve past applications |  | Not Started | FALSE
Implement Search and Filter logic for Applications | Allow filtering by status, profile, etc. |  | Not Started | FALSE
Develop Recruiter UI for Job Application Management | UI to paste link and view history |  | Not Started | FALSE
Implement Export Data functionality (Optional) | Allow exporting application data to CSV/Excel |  | Not Started | FALSE

## Duplicate_Detection
Task | Remark | Date | Status | Completed
Define Unique Constraints in Database | Prevent duplicate job links per client profile at DB level |  | Not Started | FALSE
Implement Application-level validation | Check for duplicates before DB insertion |  | Not Started | FALSE
Create API response handling for duplicates | Return appropriate error codes and messages |  | Not Started | FALSE
Develop Frontend UI to notify user of duplicates | Show clear error message when duplicate is detected |  | Not Started | FALSE
Write Unit Tests for Duplicate Detection Logic | Ensure duplicate prevention works as expected |  | Not Started | FALSE

## Analytics_Dashboard
Task | Remark | Date | Status | Completed
Create APIs to calculate Admin Dashboard Metrics | Total Assigned Profiles, Total Applications |  | Not Started | FALSE
Implement logic for Profile-wise Application Count | Calculate applications per profile |  | Not Started | FALSE
Implement logic for Recruiter Last Active Time | Track when recruiter last performed an action |  | Not Started | FALSE
Develop Admin Analytics Dashboard UI | Create visual representation of metrics |  | Not Started | FALSE
Implement Expandable Recruiter View in UI | Allow deep dive into individual recruiter stats |  | Not Started | FALSE
Add Search, Sorting, and Filtering to Dashboard | Enable easy navigation of analytics data |  | Not Started | FALSE

## Shift_Logic
Task | Remark | Date | Status | Completed
Create Reusable Service for Business Shift Date | Calculate based on 7:30 PM to 4:30 AM IST shift |  | Not Started | FALSE
Integrate Shift Logic into Application Timestamp | Assign applications to correct business day |  | Not Started | FALSE
Update Analytics APIs to use Shift-Based Date filtering | Ensure dashboard metrics follow shift logic |  | Not Started | FALSE
Write Unit Tests for Shift Logic Service | Verify correct date calculation for edge cases |  | Not Started | FALSE
Verify Shift Logic across all Daily Reports | Ensure consistency in all reporting features |  | Not Started | FALSE

## Branding_UI
Task | Remark | Date | Status | Completed
Create Reusable Mayzax Branding Components | Include Mayzax logo and color scheme |  | Not Started | FALSE
Implement Global Application Header | Display Mayzax name prominently |  | Not Started | FALSE
Ensure UI is Clean, Modern, and Responsive | Follow best practices for web design |  | Not Started | FALSE
Apply Consistent Theming across all modules | Maintain visual cohesion throughout app |  | Not Started | FALSE
Perform Cross-Browser UI Testing | Verify layout works on different devices and browsers |  | Not Started | FALSE